## Home
Product Name |  | MAHFIL | TC Start Date | 2024-05-05 | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | HOME | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By | Anasua Mazumder | Browser (tested) | [5 empty] | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | [5 empty] | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 | USER MANAGEMENT | UI Testing | HOME | Verify mahfil app open properly | Should be open Mahfil home page | Found as per expectation | N/A | 1.Go to playstore. 2. Type Mahfil in the Search option. |  |  |  | passed
2 |  |  |  | Verify Home page all content are visible properly | should be visible | Found as per expectation | N/A |  |  |  |  | passed
3 |  |  |  | Check for spelling mistake | Should not any spelling mistake | Found as per expectation | N/A |  |  |  |  | passed
4 |  |  |  | Check for grammatical mistakes | Should not any grammatical mistake | Found as per expectation | N/A |  |  |  |  | passed
5 |  |  |  | Check for front size & color | should be as par clint requirment | Found as per expectation | N/A |  |  |  |  | passed
6 |  |  |  | verify text is not overllapping | should not overrllap | Found as per expectation | N/A |  |  |  |  | passed
7 |  |  |  | verify all button are visiable properly | should be visible | Found as per expectation | N/A |  |  |  |  | passed
8 |  |  |  | Touch all button | should be touchable | Found as per expectation | N/A | 1.Touch all type of option |  |  |  | passed
9 |  |  |  | check all button are work properly | should be work properly | Found as per expectation | N/A | 1.Touch all type of option |  |  |  | passed
10 |  |  |  | check Correct label is displayed on the button | should be perfect | Found as per expectation | N/A |  |  |  |  | passed
11 |  |  |  | check all button are not overllaping each other | should not overllap | Found as per expectation | N/A |  |  |  |  | passed
12 |  |  |  | Check videos are getting displayed on home page | should be display on home page | Found as per expectation | N/A |  |  |  |  | passed
13 |  |  |  | Check good resolution videos are used | should be display on home page | Found as per expectation | N/A |  |  |  |  | passed
14 |  |  |  | Touch videos on home page | should be Touchable | Found as per expectation | N/A | 1.Touch all videos |  |  |  | passed
15 |  |  |  | Check Size of the videos | should be same size | Found as per expectation | N/A |  |  |  |  | passed
16 |  |  |  | Check vertical and horizontal scroll bars | should be scroll properly | Found as per expectation | N/A |  |  |  |  | passed
17 |  |  |  | Check mahfil logo is visible on top of the home page | should be visible on top of the home page | Found as per expectation | N/A |  |  |  |  | passed
18 |  |  |  | touch the hyperlink | should be touchable | Found as per expectation | N/A |  |  |  |  | passed
19 |  |  |  | Check hyperlink take us to correct place | should go the correct place | Found as per expectation | N/A |  |  |  |  | passed
20 |  |  |  | check popular channels | should be visible | Found as per expectation | [5 empty] | passed

## SignUp
Product Name |  | Mahfil | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Sign up | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | should not spelling & grammatical mistake | Found as per expectation | N/A |  |  |  |  | passed
2 |  |  |  | Verifying the font, text color and style | should be as per clint requirment | Found as per expectation | N/A |  |  |  |  | passed
3 |  |  |  | Check text is readable | should be readable | Found as per expectation | N/A |  |  |  |  | passed
4 |  |  |  | check text is not going outside the box | should not going outside | Found as per expectation | N/A |  |  |  |  | passed
5 |  |  |  | Check correct labels are displayed for the text field | should be displayed | Found as per expectation | N/A |  |  |  |  | passed
6 |  |  |  | Checking 'country code' field is not enabled by default | should not be enable by default | Found as per expectation | N/A |  |  |  |  | passed
7 |  |  |  | Check arrow sign shows on the dropdown | should be displayed | Found as per expectation | N/A |  |  |  |  | passed
8 |  |  |  | Check arrow sign shows on the top | should be on the top | Found as per expectation | N/A |  |  |  |  | passed
9 |  |  |  | Check sign in with google hyperlink work properly | should be google hyperlink work properly | Found as per expectation | N/A |  |  |  |  | passed
10 |  |  |  | Check sign in with email hyperlink work properly | should be email hyperlink work properly | Found as per expectation | N/A |  |  |  |  | passed
11 |  |  |  | Check sign in with anaother way hyperlink work properly | should be another way hyperlink work properly | Found as per expectation | N/A |  |  |  |  | passed
12 |  |  |  | verify sign up icon is visible on top of home page | should be visible | Found as per expectation | N/A |  |  |  |  | passed
13 |  | Func |  | verify sign up icon is work properly | should be work properly | Found as per expectation | N/A |  |  |  |  | passed
|  |  |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue with Email 3.Keep mandatory fields blank
|  |  |  | Entering invalid email for email field | Should not accept the provided input& should pop an error massage | Not found as per expectation | gghhh@hjk.com | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue with Email 3.enter invalid email | https://shorturl.at/GPcUK |  |  | Fail
|  |  |  | Checking alert message for email mandatory fields | Should pop an error message | Not found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue with Email 3.enter blank in email fild | https://shorturl.at/tOaqN |  |  | Fail
|  |  |  | Check Phone number field allow any special characters | Show the error massage only accept the digits | Not found as per expectation | ##**))##/ | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter special characters | https://shorturl.at/M1cvw |  |  | Fail
|  |  |  | Check phone number field allow any alphabets | Show the error massage only accept the digits | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter special characters |  |  |  | passed
|  |  |  | Check number field allow integer number or digits | should accept | found as per expectation | 123577887 | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter special characters |  |  |  | passed
|  |  |  | Keeping mandatory fields blank in phone number field | should not accept | not found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter blank and touch continue button | https://shorturl.at/PiOC0 |  |  | Fail
|  | Boundary Value analysis Techniques |  | Check number field have any BVA | Accept only 10 digits | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3. |  |  |  | passed
|  |  |  | Check number field allow 9 digits | Should not accept | found as per expectation | 123456789 | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 9 digits |  |  |  | passed
|  |  |  | Check number field allow 11 digits | Should not accept | found as per expectation | 12345678912 | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 11 digits |  |  |  | passed
|  |  |  | Check number field accept 10 valid digits | visible new interface enter OTP | found as per expectation | 1234567891 | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 10 digits |  |  |  | passed
|  |  |  | Check OTP field allow invalid OTP | Alert show invalid OTP | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 10 digits |  |  |  | passed
|  |  |  | Check OTP field allow any special characters or alphabets | Alert show invalid OTP | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 10 digits |  |  |  | passed
|  |  |  | Check OTP field Accept expired OTP | Shouldn’t accept | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 10 digits |  |  |  | passed
|  |  |  | Check OTP has a timelimit | OTP time limit is 120 sec | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 10 digits |  |  |  | passed
|  |  |  | Check have Resend OTP option | Have the resend OTP option | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 10 digits |  |  |  | passed
|  |  |  | Check OTP field accept valid OTP | Accept valid OTP | found as per expectation |  | 1. Goto the playstore& search Mahfil 2. go to home page & touch on signup icon at the top of the corner. 3.Touch continue another way 3.enter 10 digits |  |  |  | passed
|  | Decision table Techniques |  | Check After giving valid OTP continue button work properly | visible a new interface called sign up your account | found as per expectation | [5 empty] | passed
|  |  |  | Check name field allow only special characters | should not allow any special characters | not found as per expectation | ##@#@*** | 1.enter special character in name field | https://shorturl.at/7rAVm |  |  | fail
|  |  |  | Check name field allow only numbers | should not allow | not found as per expectation | 1234 | 1.enter number in name field | https://shorturl.at/w0Fvw |  |  | fail
|  |  |  | Check name field allow valid name | should be Accept the valid name | found as per expectation |  | 1.enter valid namein name field |  |  |  | passed
|  | Boundary Value analysis Techniques |  | Check name field have any BVA | should be Accept only 3-50 characters | found as per expectation |  | 1.enter more than 2 characters in name field |  |  |  | passed
|  |  |  | Check name field allow 2 characters | should not Accept | found as per expectation |  | 1.enter 2 characters in name field |  |  |  | passed
|  |  |  | Check name field allow 3 characters | should be Accept | found as per expectation |  | 1.enter 3 characters in name field |  |  |  | passed
|  |  |  | Check name field allow max 50 characters | should be Accept | found as per expectation |  | 1.enter max 50 characters in name field |  |  |  | passed
|  |  |  | Check name field allow 51 characters | should not Accept | found as per expectation |  | 1.enter 51 characters in name field |  |  |  | passed
|  |  |  | Check Email field allow only number or special characters | should not Accept | not found as per expectation | 11111@12233 | 1.enter number in name field | https://shorturl.at/0UwIL |  |  | fail
|  |  |  | Check email field allow valid emial | should be accepted | found as per expectation |  | 1.enter valid email in name field |  |  |  | passed
|  | Decision table Techniques |  | Check continue button work properly | Successfully Signup | found as per expectation |  | 1.Touch continue button |  |  |  | passed

## Login
Product Name |  | Mahfil | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Login | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By | Anasua | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Functionality Testing | Login | Check Sign in with google link work properly | should be login successfully | Found as per expectation | [5 empty] | passed
2 |  |  |  | Check phone number field all Checklist as same as signup | Should be ok | Found as per expectation | [5 empty] | passed
3 |  |  |  | Check OTP field all Checklist as same as signup | Should be ok | Found as per expectation | [5 empty] | passed
4 |  |  |  | Check successfully Enter the number and Enter OTP | should be Login successfully | Found as per expectation | [5 empty] | passed
5 |  |  |  | check sign in with email link work properly | should be login successfully | Found as per expectation | [5 empty] | passed
6 |  |  |  | check successfully enter valid email | should be login | Found as per expectation | [5 empty] | passed

## Content Categories
Product Name |  | Mahfil App | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Content Categories | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Functionality Testing | Content Categories | Check all content categories button | Should be okay | Found as per expectation | [5 empty] | passed
2 |  |  |  | Check all content categories button work properly | should take us to the right content | Found as per expectation | [5 empty] | passed
3 |  |  |  | Check Lecture content button is work properly | should take us to the lecture videos list | Found as per expectation | [5 empty] | passed
4 |  |  |  | Check Lecture content catagorie properly organised | In this catagories all videos are islamic lecture related | Found as per expectation | [5 empty] | passed
5 |  |  |  | Check touch to the any lecture video | Should open the video without any interrupt | Found as per expectation | [5 empty] | passed
6 |  |  |  | Check all videos audio, quility and and playback speed work | Should work | Found as per expectation | [5 empty] | passed
7 |  |  |  | Verify Nasheed content button work properly | should Take us to the nasheed video list | Found as per expectation | [5 empty] | passed
8 |  |  |  | Check nasheed content are correctly organised | In this content all videos are nasheed related | Found as per expectation | [5 empty] | passed
9 |  |  |  | Check touch or tap to the any nasheed video | Should open the videos | Found as per expectation | [5 empty] | passed
10 |  |  |  | Verify telawat content button is accessible | should take us to the telawat videos list | Found as per expectation | [5 empty] | passed
11 |  |  |  | Check all telawat content are properly organised | In this content all videos are telawat related videos | Found as per expectation | [5 empty] | passed
12 |  |  |  | Check touch or tap to the telawat videos | Should open the videos | Found as per expectation | [5 empty] | passed
13 |  |  |  | Verify Others content button is accessible | Take us to the all mixed videos playlist | Found as per expectation | [5 empty] | passed
14 |  |  |  | Check all other content are properly organised | Should be organised | Found as per expectation | [5 empty] | passed
15 |  |  |  | Check touch or tap to the all other videos | Should open the videos | Found as per expectation | [5 empty] | passed

## Video Streaming
Product Name |  | Mahfil App | TC Start Date |  | TC Execution Start Date | 17/09/2022 |  |  |  |  | TEST CASE
Module Name |  | Video Streaming | TC End Date |  | TC Execution End Date | 18/09/2022 |  |  |  |  | PASS | #REF!
Epic |  |  | Test Case Developed By | Anasua | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Functionality Testing | Video Streaming | Verify lecture content all videos open successfully | Should be open | Found as per expectation | [5 empty] | passed
2 |  |  |  | Check all Lecture videos should be pause ,play & autoplay | Should ok | Found as per expectation | [5 empty] | passed
3 |  |  |  | Check all lecture videos playback speed & quality & audio work properly | Should all videos playback speed and quility and audio by default are ok | Found as per expectation | [5 empty] | passed
4 |  |  |  | Check videos 10 sec forward and backword method work properly | Should be work properly | Found as per expectation | [5 empty] | passed
5 |  |  |  | Check sound mute option work properly | Should work properly | Found as per expectation | [5 empty] | passed
6 |  |  |  | Check full screen video option work properly | Should work properly | Found as per expectation | [5 empty] | passed
|  |  |  | check autoplay option work properly | Should work properly | Found as per expectation
7 |  |  |  | Verify nasheed content all videos open successfully | Should be okay | Found as per expectation | [5 empty] | passed
Found as per expectation
8 |  |  |  | Check all nasheed videos will be pause ,play and autoplay | Should okay | Found as per expectation | [5 empty] | passed
9 |  |  |  | Check all nasheed videos playback speed & quality method & audio work properly | Should all videos playback speed quility & audio by default are okay | Found as per expectation | [5 empty] | passed
10 |  |  |  | Check videos 10 sec forward and backword method work properly | Should work properly | Found as per expectation | [5 empty] | passed
11 |  |  |  | Check sound mute option work properly | Should ok | Found as per expectation | [5 empty] | passed
12 |  |  |  | Check full screen video option work properly | Should work properly | Found as per expectation | [5 empty] | passed
13 |  |  |  | Verify telawat content all videos open successfully | Should start the video without any buffering issues | Found as per expectation | [5 empty] | passed
14 |  |  |  | Check all telawat videos will be pause ,play and autoplay | Should ok | Found as per expectation | [5 empty] | passed
15 |  |  |  | Check all telawat videos playback speed & quality method work properly | Should all videos playback speed and quility are ok | Found as per expectation | [5 empty] | passed
16 |  |  |  | Check videos 10 sec forward and backword method work properly | Should work properly | Found as per expectation | [5 empty] | passed
17 |  |  |  | Check sound mute option work properly | Should ok | Found as per expectation | [5 empty] | passed
18 |  |  |  | Check full screen video option work properly | Should work properly | Found as per expectation | [5 empty] | passed
19 |  |  |  | Verify other content all videos open successfully | Should start the video without any buffering issues | Found as per expectation | [5 empty] | passed
20 |  |  |  | Check all other videos will be pause ,play and autoplay | Should ok | Found as per expectation | [5 empty] | passed
21 |  |  |  | Check all other videos playback speed & quality method work properly | Should all videos playback speed and quility are ok | Found as per expectation | [5 empty] | passed
22 |  |  |  | Check videos 10 sec forward and backword method work properly | Should ok | Found as per expectation | [5 empty] | passed
23 |  |  |  | Check sound mute option work properly | Should work properly | Found as per expectation | [5 empty] | passed
24 |  |  |  | Check full screen video option work properly | Should work properly | Found as per expectation | [5 empty] | passed
25 |  |  |  | Verify lecture video content subtitle option work properly and show subtaitle | Should be work | not Found as per expectation |  |  | https://shorturl.at/rbIlZ |  |  | fail
26 |  |  |  | Verify nasheed video content subtitle option work properlyand show subtaitle | Should be work | not Found as per expectation |  |  | https://shorturl.at/rbIlZ |  |  | fail
27 |  |  |  | Verify Telawat video content support subtitle | Should support | not Found as per expectation |  |  | https://shorturl.at/rbIlZ |  |  | fail
28 |  |  |  | Verify other video content support subtitle | Should support | not Found as per expectation |  |  | https://shorturl.at/rbIlZ |  |  | fail
|  |  |  | Verify All type method like mashallah, link,download and more option are touchable and any work fine | should be work properly | found as per expectation | [5 empty] | passed
29

## Download
Product Name |  | Mahfil | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Download | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By | Anasua | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Functionality Testing | Download | Verify any content videos download button work properly | should be work properly | found as per expectation |  | 1. Click on a Video 2. Click on Download button |  |  |  | passed
2 |  |  |  | Verify user can download any videos | should download all videoa | not found as per expectation |  | 1. Click on a Video 2. Click on Download button | https://shorturl.at/Jq2O6 |  |  | fail
3 |  |  |  | Validate Download Functionality without Premium. | 1. should Display a pop-up cart. 2. should Suggested for get Premium in Pop-up cart | found as per expectation |  | 1. Click on a Video 2. Click on Download button |  |  |  | passed
4 |  |  |  | Validate Download Functionality with Premium. | 1. Display "Download has Started. Please wait a moment 2. Download completed. 3.Display All Download video in Downloads section. 4. Video plays in off line without any issues. | found as per expectation |  | . Click on a Video 2. Click on Download button. 3. Click on menu icon 4. Click on Download Option. 5. Click on a video and click pause then play. 6. Turn off internet and click on see download video and play a video. |  |  |  | passed
5 |  |  |  | Validate Download Functionality in same video which is downloaded with Premium. | 1. Display "Download already downloaded". 2.Display All Download video in Downloads section. 3. Video plays in off line without any issues. | found as per expection |  | . Click on a Video 2. Click on Download button. 3. Click on menu icon 4. Click on Download Option. 5. Click on a video and click pause then play. 6. Turn off internet and click on see download video and play a video. |  |  |  | passed
6 |  |  |  | verify premium options pages display with all package and all package are clickable | should be visible and work fine | found as per expectation |  | . Click on a Video 2. Click on Download button. 3. click next option 4. display all package |  |  |  | passed

## Search and Filters
Product Name |  | Mahfil | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Search and Filters | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Functionality Testing | Search and Filters | Verify serach option is a text field | Should text field | found as per expectation | [5 empty] | passed
2 |  |  |  | Check serch text field allow input | Should allow input | found as per expectation | [5 empty] | passed
3 |  |  |  | Check text field allow special characters, alphabets and digits | Should allow | found as per expectation | [5 empty] | passed
4 |  |  |  | Check using search field user can find the specific content | Should find the specific content | found as per expectation | [5 empty] | passed
5 |  |  |  | Check user can use filter like catagories, date ,popularity for find accurate content | Should Have the filter option | found as per expectation | [5 empty] | Inproving area

## User Interaction
Product Name |  | Mahfil | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | User Interaction | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Functionality Testing | User Interaction | Verify like ,comment, and share option are available | Should available all the option | found as per executation |  | 1. Click on a video. 2. Click on the like button 3. Click on comment input box and write comment. 4. click sent icon. 5. swip down the comment section and click on more button , click share. |  |  |  | passed
2 |  |  |  | Check add to fabourite option is available | Should available | found as per executation |  | 1. Click on a video. 2. Click on the like button 3. Click on comment input box and write comment. 4. click sent icon. 5. swip down the comment section and click on more button , click share. |  |  |  | passed
3 |  |  |  | Check user can like, comment & share the videos | Should Work all the option | found as per executation |  | 1. Click on a video. 2. Click on the like button 3. Click on comment input box and write comment. 4. click sent icon. 5. swip down the comment section and click on more button , click share. |  |  |  | passed
4 |  |  |  | Check notification for all the action genarated successfully | Should Genarated successfully | found as per executation |  | 1. Click on a video. 2. Click on the like button 3. Click on comment input box and write comment. 4. click sent icon. 5. swip down the comment section and click on more button , click share. |  |  |  | passed
5 |  |  |  | Verify that user interaction reflected corectly | Should ok | found as per executation |  | 1. Click on a video. 2. Click on the like button 3. Click on comment input box and write comment. 4. click sent icon. 5. swip down the comment section and click on more button , click share. |  |  |  | passed
6 |  |  |  | Validate features that allow users to share videos in Messenger | Should be okay | found as per executation |  | . Click on a video. 2. click on more button , click share. 3. Click messenger , select a person. 4. click sent icon. |  |  |  | passed
7 |  |  |  | Validate features that allow users to share videos in whatsapp | should be okay | found as per executation |  | . Click on a video. 2. click on more button , click share. 3. Click messenger , select a person. 4. click sent icon. |  |  |  | passed
8 |  |  |  | Validate features that allow users to share videos in instagram | should be okay | found as per executation |  | . Click on a video. 2. click on more button , click share. 3. Click messenger , select a person. 4. click sent icon. |  |  |  | passed

## performance Testing
Product Name |  | Mahfil | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  |  | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | performance Testing |  | Check apps performance during video playback | Should okay | found as per executation | N/A | 1.scroll the app 2. Click on a video 3. Click on download. |  |  |  | passed
2 |  |  |  | Check performance during playback when multiple threads hit the app | Should okay | found as per executation | N/A | 1.scroll the app 2. Click on a video 3. Click on download. |  |  |  | passed
3 |  |  |  | Verify apps performance during downloading | Should okay | found as per executation | N/A | 1.scroll the app 2. Click on a video 3. Click on download. |  |  |  | passed

## Unique Video Content
Product Name |  | Mahfil | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Unique Video Content | TC End Date |  | TC Execution End Date | [5 empty] | PASS | #REF!
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | #REF!
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Functionality Testing | Unique Video Content | Verify content available in the app | All content are islamic related | found as per expectation | [5 empty] | passed
2 |  |  |  | Verify content are aligns with islamic principle | Should okay | found as per expectation | [5 empty] | passed
3 |  |  |  | Check for duplicate content | Should all content are original | found as per expectation | [5 empty] | passed